## Slide 1: Development Plan Images

## Slide 2: Development Plan
Area 1
Initiative 1.1
Initiative 1.2
Area 2
… etc …
Success Criteria
… etc …
Initiative 2.1
… etc …
Success Criteria
… etc …
Action Plan
… etc …
… etc …
Action Plan

## Slide 3: Areas and Initiatives
Quality of Education
Improving Teaching and Learning
Improving SEND support
Behaviour and Attitudes
Success Criteria
Improving Attendance
Improving Behaviour
Success Criteria
… etc …
Action Plan
… etc …
Action Plan
Personal Development
Increasing Extra-curricular involvement

## Slide 4: Initiative Detail
Improving Attendance
Owner/Leader Jane Bloggs
Rationale Students not in school, particularly disadvantaged, make less progress and development. Particularly where the absence is persistent.
Resources 2 days per week EWO
New attendance officer position
Monitoring Weekly by DHT and SLT
Half termly by EWO
Termly at Governors meeting
Supported by John Doe

## Slide 5: Initiative Success Criteria and Action Plans
Action Plans
What | Who | When | Done
Appoint to new post | DHT | Sep 30 | Yes
Meet PA students | EWO | Oct 22 | Yes
Issue fines for Holidays | SBB | Nov 30 | Yes
Meet PA students | EWO | Feb 14 | No
Issue certificates | HT | Jul 15 | No
Success Criteria
School attendance for the year will improve by 1% to 96%
  A stomach bug impacted Y7 and Y8 for a month in December!
    Partially met
Description
  Notes
    Status
Description
  Notes
    Status

## Slide 6: Development Plan Dashboard Panel